## Sheet2
L1 | L2 | L3 | L4 | L5 | L6 | Activity Code | Activity Description | Start Date | complete_pct_type | task_type | duration_type | review_type | status_code | driving_path_flag | cstr_type | Critical | Cat_Rem_Dur | Cat_Tot_Flo | BL Today | End_Date | Activity Status | Critical Services | RemainCat | TotalFloatCat
2 - DELIVERY PHASE | 8 - Construction | 2 - Utility Service Relocations | 2 - Service Relocation - South of River Beach Street | 4 - Demolition works |  | UT-S2-2350 | FPO101/ATOM101/102/103 Remove redundant services | 46197 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | N | 46212 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 4 - Road Commissioning |  | CO-S1-24550 | Complete Road Safety Audit and Complete Punchlist Items | 46342 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | Y |  | Yes | 30-60 | 0-30 | Y | 46379 | Not Started | Critical | 20 and Over | 0-10
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 4 - Road Commissioning |  | CO-S1-3860 | Test and Commission ITS/Electrical/Road/Arch Lightings & Traffic Lights | 46342 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | Y |  | Yes | 0-30 | 0-30 | N | 46372 | Not Started | Critical | 20 and Over | 0-10
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 3 - Handover | 1 - Walkdowns |  | CO-S1-5100 | Walkdown - Balance for Open for Traffic | 46308 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 60 and above | Y | 46308 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 3 - Handover | 1 - Walkdowns |  | CO-S1-5110 | Walkdown - Balance for Bridge Completion | 46375 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 60 and above | Y | 46376 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 3 - Handover | 1 - Walkdowns |  | CO-S1-5120 | Walkdown - Balance for Practical Completion | 46375 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 60 and above | Y | 46376 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 3 - Handover | 2 - SWTC Handover |  | CO-S1-34810 | Remaining Works for Project Handover | 46388 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | Y |  | Yes | 60 and above | 0-30 | Y | 46449 | Not Started | Critical | 20 and Over | 0-10
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 3 - Handover | 2 - SWTC Handover |  | CO-S1-3870 | Submit Design Documentation, Certifications, Surveys, As Constructed Information & Drawings and All Other Documentation | 46380 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | Y |  | Yes | 0-30 | 0-30 | N | 46387 | Not Started | Critical | 0-10 | 0-10
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 3 - Handover | 2 - SWTC Handover |  | CO-S1-3880 | Practical Completion of SP1 | 46387 | CP_Phys | TT_FinMile | DT_FixedDrtn | RV_OK | TK_NotStart | N |  |  | 0-30 | 60 and above | N | 46387 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 3 - Handover | 2 - SWTC Handover |  | CO-S1-3890 | 01 - Pavement Condition Performance Criteria | 46340 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 60 and above | Y | 46359 | Not Started | Not Critical | 10-20 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 3 - Handover | 2 - SWTC Handover |  | CO-S1-3900 | 02 - Settlement and Movement Data (Pavement) | 46340 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 60 and above | Y | 46359 | Not Started | Not Critical | 10-20 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 3 - Handover | 2 - SWTC Handover |  | CO-S1-3910 | 03 - Settlement and Movement Data (Structures) | 46288 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N | CS_ALAP |  | 60 and above | 60 and above | Y | 46387 | Not Started | Not Critical | 20 and Over | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 3 - Handover | 2 - SWTC Handover |  | CO-S1-3940 | 06 - Survey Data including Cadastral Data | 46288 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N | CS_ALAP |  | 60 and above | 60 and above | Y | 46387 | Not Started | Not Critical | 20 and Over | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 3 - Handover | 2 - SWTC Handover |  | CO-S1-3950 | 07 - Load Rating of Structures | 46288 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N | CS_ALAP |  | 60 and above | 60 and above | Y | 46387 | Not Started | Not Critical | 20 and Over | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 3 - Handover | 2 - SWTC Handover |  | CO-S1-3970 | 09 - Approvals for Signs and Pavement Markings | 46370 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | Y | CS_ALAP | Yes | 0-30 | 0-30 | Y | 46379 | Not Started | Critical | 0-10 | 0-10
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 3 - Handover | 2 - SWTC Handover |  | CO-S1-3980 | 10 - Sign Warranties | 46289 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 60 and above | 60 and above | Y | 46358 | Not Started | Not Critical | 20 and Over | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 3 - Handover | 2 - SWTC Handover |  | CO-S1-3990 | 11 - Road Safety Audits | 46310 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | Y | CS_ALAP | Yes | 60 and above | 0-30 | Y | 46379 | Not Started | Critical | 20 and Over | 0-10
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 3 - Handover | 2 - SWTC Handover |  | CO-S1-4030 | 14 - Acceptance of lighting from the LGA and Western Power | 46318 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N | CS_ALAP |  | 60 and above | 60 and above | Y | 46387 | Not Started | Not Critical | 20 and Over | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 3 - Handover | 2 - SWTC Handover |  | CO-S1-4040 | 15 - Approvals for Traffic Control Signals | 46212 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | Y | CS_ALAP | Yes | 60 and above | 0-30 | Y | 46281 | Not Started | Critical | 20 and Over | 0-10
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 3 - Handover | 2 - SWTC Handover |  | CO-S1-4050 | 16 - Approvals for Works in the Vicinity of Services | 46326 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | Y | CS_ALAP | Yes | 30-60 | 0-30 | Y | 46379 | Not Started | Critical | 20 and Over | 0-10
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 3 - Handover | 2 - SWTC Handover |  | CO-S1-4060 | 17 - Acceptance of Works from the LGA | 46329 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | Y | CS_ALAP | Yes | 30-60 | 0-30 | Y | 46379 | Not Started | Critical | 20 and Over | 0-10
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 3 - Handover | 2 - SWTC Handover |  | CO-S1-4090 | 20 - Approvals to Operate Vehicles with Excess Mass | 46300 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | Y | CS_ALAP | Yes | 30-60 | 0-30 | Y | 46339 | Not Started | Critical | 20 and Over | 0-10
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 3 - Handover | 2 - SWTC Handover |  | CO-S1-5010 | 22 - Maintenance Reports | 46370 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | Y | CS_ALAP | Yes | 0-30 | 0-30 | Y | 46379 | Not Started | Critical | 0-10 | 0-10
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 4 - Civil Improvement Works | 3 - Civil Reinstatement Works |  | CO-S1-34330 | Stirling/REDACTED Hwy Reinstatement | 46328 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N | CS_MSOA |  | 30-60 | 0-30 | Y | 46374 | Not Started | Critical | 20 and Over | 0-10
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 4 - Civil Improvement Works | 3 - Civil Reinstatement Works |  | CO-S1-34340 | REDACTED Hwy & REDACTED St Turn Pocket Reinstatement | 46356 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N | CS_MSOA |  | 0-30 | 0-30 | Y | 46374 | Not Started | Critical | 10-20 | 0-10
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 4 - Civil Improvement Works | 3 - Civil Reinstatement Works |  | CO-S1-34350 | Marmion & East Reinstatement | 46363 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N | CS_MSOA |  | 0-30 | 0-30 | Y | 46374 | Not Started | Critical | 0-10 | 0-10
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 4 - Civil Improvement Works | 3 - Civil Reinstatement Works |  | CO-S1-34360 | REDACTED Hwy (between QVS and REDACTED Hwy) Reinstatement | 46349 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N | CS_MSOA |  | 0-30 | 0-30 | Y | 46374 | Not Started | Critical | 10-20 | 0-10
2 - DELIVERY PHASE | 8 - Construction | 5 - SP2 - Landscaping & Revegetation | 1 - Landscaping & Revegetation | 1 - South of River - North of REDACTED St |  | CO-S2-1060 | SOR / Nth of REDACTED St - Hard Landscaping (incl. Furniture & Fixings) | 46311 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | N | 46319 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 5 - SP2 - Landscaping & Revegetation | 1 - Landscaping & Revegetation | 1 - South of River - North of REDACTED St |  | CO-S2-1070 | SOR / Nth of REDACTED St - Soft Landscaping | 46293 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | N | 46308 | Not Started | Not Critical | 10-20 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 5 - SP2 - Landscaping & Revegetation | 1 - Landscaping & Revegetation | 1 - South of River - North of REDACTED St |  | CO-S2-1120 | SOR - Footpath FRP North of REDACTED St (SE) | 46286 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | Y | 46310 | Not Started | Not Critical | 10-20 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 5 - SP2 - Landscaping & Revegetation | 1 - Landscaping & Revegetation | 1 - South of River - North of REDACTED St |  | CO-S2-1140 | Installation of Public Art Commission 1 (Barrier Pattern) | 46251 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 60 and above | Y | 46288 | Not Started | Not Critical | 20 and Over | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 5 - SP2 - Landscaping & Revegetation | 1 - Landscaping & Revegetation | 1 - South of River - North of REDACTED St |  | CO-S2-1210 | SOR - Footpath FRP North of REDACTED St (SW) | 46228 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 60 and above | Y | 46241 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 5 - SP2 - Landscaping & Revegetation | 1 - Landscaping & Revegetation | 2 - South of River - South of REDACTED St |  | CO-S1-33770 | Installation of Public Art Commission 2 (Waugyl Sculpture) | 46288 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | Y | 46305 | Not Started | Not Critical | 10-20 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 5 - SP2 - Landscaping & Revegetation | 1 - Landscaping & Revegetation | 2 - South of River - South of REDACTED St |  | CO-S2-1080 | SOR - Footpath FRP South of REDACTED St (SE) | 46244 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | N | 46266 | Not Started | Not Critical | 10-20 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 5 - SP2 - Landscaping & Revegetation | 1 - Landscaping & Revegetation | 2 - South of River - South of REDACTED St |  | CO-S2-1090 | SOR / Sth of REDACTED St - Soft Landscaping | 46284 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | N | 46291 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 5 - SP2 - Landscaping & Revegetation | 1 - Landscaping & Revegetation | 2 - South of River - South of REDACTED St |  | CO-S2-1200 | SOR - Footpath FRP South of REDACTED St (SW) | 46228 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 60 and above | Y | 46239 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 5 - SP2 - Landscaping & Revegetation | 1 - Landscaping & Revegetation | 3 - North of River |  | CO-S2-1050 | NOR - Soft Landscaping | 46283 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 0-30 | N | 46316 | Not Started | Not Critical | 20 and Over | 10-20
2 - DELIVERY PHASE | 8 - Construction | 5 - SP2 - Landscaping & Revegetation | 1 - Landscaping & Revegetation | 3 - North of River |  | CO-S2-1100 | NOR - Footpath FRP | 46283 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 0-30 | Y | 46325 | Not Started | Not Critical | 20 and Over | 10-20
2 - DELIVERY PHASE | 8 - Construction | 5 - SP2 - Landscaping & Revegetation | 1 - Landscaping & Revegetation | 3 - North of River |  | CO-S2-1110 | NOR - Footpath Pavers | 46283 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 0-30 | Y | 46325 | Not Started | Not Critical | 20 and Over | 10-20
2 - DELIVERY PHASE | 8 - Construction | 5 - SP2 - Landscaping & Revegetation | 1 - Landscaping & Revegetation | 3 - North of River |  | CO-S2-1220 | NOR - Rock pitching | 46265 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 0-30 | Y | 46269 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 5 - SP2 - Landscaping & Revegetation | 1 - Landscaping & Revegetation | 4 - Architectural Lighting Programming |  | CO-S2-1150 | Sequence Production | 46218 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 60 and above | Y | 46239 | Not Started | Not Critical | 10-20 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 5 - SP2 - Landscaping & Revegetation | 1 - Landscaping & Revegetation | 4 - Architectural Lighting Programming |  | CO-S2-1160 | Installation Planning | 46239 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 60 and above | Y | 46260 | Not Started | Not Critical | 10-20 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 5 - SP2 - Landscaping & Revegetation | 1 - Landscaping & Revegetation | 4 - Architectural Lighting Programming |  | CO-S2-1170 | On-Site Testing | 46260 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 60 and above | Y | 46274 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 5 - SP2 - Landscaping & Revegetation | 1 - Landscaping & Revegetation | 4 - Architectural Lighting Programming |  | CO-S2-1180 | Adjustments | 46274 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 60 and above | Y | 46281 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 5 - SP2 - Landscaping & Revegetation | 1 - Landscaping & Revegetation | 4 - Architectural Lighting Programming |  | CO-S2-1190 | Display Commissioning (post-system energization) | 46373 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | Y | 46393 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 5 - SP2 - Landscaping & Revegetation | 2 - Handover |  |  | CO-S2-1000 | COMM - Landscape & Irrigation - SAT Testing | 46328 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 0-30 | N | 46339 | Not Started | Not Critical | 0-10 | 10-20
2 - DELIVERY PHASE | 8 - Construction | 5 - SP2 - Landscaping & Revegetation | 2 - Handover |  |  | CO-S2-1010 | COMM - Landscape & Irrigation - SIT Testing | 46342 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 0-30 | N | 46353 | Not Started | Not Critical | 0-10 | 10-20
2 - DELIVERY PHASE | 8 - Construction | 5 - SP2 - Landscaping & Revegetation | 2 - Handover |  |  | CO-S2-1030 | Submit Design Documentation, Certifications, Surveys, As Constructed Information & Drawings and All Other Documentation | 46354 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 60 and above | 0-30 | N | 46423 | Not Started | Not Critical | 20 and Over | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 5 - SP2 - Landscaping & Revegetation | 2 - Handover |  |  | CO-S2-1040 | Practical Completion of SP2 | 46423 | CP_Phys | TT_FinMile | DT_FixedDrtn | RV_OK | TK_NotStart | N |  |  | 0-30 | 0-30 | N | 46423 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 3 - Superstructure - Demolition and Deck Install | 1 - Bridge Demolition | CO-S1-22970 | Demolition Complete | 46252 | CP_Phys | TT_FinMile | DT_FixedDrtn | RV_OK | TK_NotStart | N |  |  | 0-30 | 60 and above | N | 46252 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 3 - Superstructure - Demolition and Deck Install | 1 - Bridge Demolition | CO-S1-33240 | Removal of Piles at Pier 12 | 46213 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 60 and above | Y | 46214 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 3 - Superstructure - Demolition and Deck Install | 1 - Bridge Demolition | CO-S1-33250 | Removal of Piles at Pier 11 | 46216 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 60 and above | Y | 46217 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 3 - Superstructure - Demolition and Deck Install | 1 - Bridge Demolition | CO-S1-33260 | Removal of Piles at Pier 10 | 46217 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 60 and above | Y | 46219 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 3 - Superstructure - Demolition and Deck Install | 1 - Bridge Demolition | CO-S1-33270 | Removal of Piles at Pier 9 | 46220 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 60 and above | Y | 46221 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 3 - Superstructure - Demolition and Deck Install | 1 - Bridge Demolition | CO-S1-33280 | Removal of Piles at Pier 8 | 46221 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 60 and above | Y | 46223 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 3 - Superstructure - Demolition and Deck Install | 1 - Bridge Demolition | CO-S1-33290 | Removal of Piles at Pier 7 | 46224 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 60 and above | Y | 46225 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 3 - Superstructure - Demolition and Deck Install | 1 - Bridge Demolition | CO-S1-33300 | Removal of Piles at Pier 6 | 46225 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 60 and above | Y | 46227 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 3 - Superstructure - Demolition and Deck Install | 1 - Bridge Demolition | CO-S1-33310 | Removal of Piles at Pier 18 | 46228 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 60 and above | Y | 46230 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 3 - Superstructure - Demolition and Deck Install | 1 - Bridge Demolition | CO-S1-33320 | Removal of Piles at Pier 19 | 46230 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 60 and above | Y | 46231 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 3 - Superstructure - Demolition and Deck Install | 1 - Bridge Demolition | CO-S1-33330 | Removal of Piles at Pier 20 | 46232 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 60 and above | Y | 46233 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 3 - Superstructure - Demolition and Deck Install | 1 - Bridge Demolition | CO-S1-33340 | Removal of Piles at Pier 21 | 46233 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 60 and above | Y | 46235 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 3 - Superstructure - Demolition and Deck Install | 1 - Bridge Demolition | CO-S1-33350 | Removal of Piles at Pier 22 | 46237 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 60 and above | Y | 46239 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 3 - Superstructure - Demolition and Deck Install | 1 - Bridge Demolition | CO-S1-33360 | Removal of Piles at Pier 13 | 46212 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 60 and above | Y | 46213 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 3 - Superstructure - Demolition and Deck Install | 1 - Bridge Demolition | CO-S1-33370 | Removal of Piles at Pier 23 | 46239 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 60 and above | Y | 46240 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 3 - Superstructure - Demolition and Deck Install | 1 - Bridge Demolition | CO-S1-33380 | Removal of Piles at Pier 24 | 46241 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 60 and above | Y | 46242 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 3 - Superstructure - Demolition and Deck Install | 1 - Bridge Demolition | CO-S1-33390 | River Survey & Debris Clean-Up | 46235 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 60 and above | Y | 46252 | Not Started | Not Critical | 10-20 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 1 - On-Bridge Road Works | 1 - Concrete Barrier | CO-S1-23340 | FRP Concrete Barrier - Deck Pour 1A | 46192 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | N | 46205 | Not Started | Not Critical | 10-20 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 1 - On-Bridge Road Works | 1 - Concrete Barrier | CO-S1-23360 | Concrete Barrier Curing Time | 46250 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | N | 46251 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 1 - On-Bridge Road Works | 1 - Concrete Barrier | CO-S1-23510 | FRP Concrete Barrier - Deck Pour 3 | 46237 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | N | 46248 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 1 - On-Bridge Road Works | 1 - Concrete Barrier | CO-S1-23530 | FRP Concrete Barrier - Deck Pour 2A | 46165 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | N | 46177 | Not Started | Not Critical | 10-20 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 1 - On-Bridge Road Works | 1 - Concrete Barrier | CO-S1-23540 | FRP Concrete Barrier - Deck Pour 4 | 46209 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | N | 46220 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 1 - On-Bridge Road Works | 1 - Concrete Barrier | CO-S1-23550 | FRP Concrete Barrier - Deck Pour 5 | 46239 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | N | 46249 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 1 - On-Bridge Road Works | 1 - Concrete Barrier | CO-S1-34730 | FRP Concrete Barrier - Deck Pour 2B | 46178 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | Y | 46192 | Not Started | Not Critical | 10-20 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 1 - On-Bridge Road Works | 1 - Concrete Barrier | CO-S1-34740 | FRP Concrete Barrier - Deck Pour 2C | 46193 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | Y | 46206 | Not Started | Not Critical | 10-20 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 1 - On-Bridge Road Works | 1 - Concrete Barrier | CO-S1-34750 | FRP Concrete Barrier - Deck Pour 1B | 46206 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | Y | 46220 | Not Started | Not Critical | 10-20 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 1 - On-Bridge Road Works | 1 - Concrete Barrier | CO-S1-34760 | FRP Concrete Barrier - Deck Pour 1C | 46221 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | Y | 46235 | Not Started | Not Critical | 10-20 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 2 - Superstructure - Edge Girders | 1 - Eastern Towers | CO-S1-24530 | Removal of Scaffold Access - Tower 2 East | 46202 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | Y | 46209 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 2 - Superstructure - Edge Girders | 1 - Eastern Towers | CO-S1-24540 | Removal of Scaffold Access - Tower 1 East | 46186 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 0-30 | Y | 46193 | Not Started | Critical | 0-10 | 0-10
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 2 - Superstructure - Edge Girders | 1 - Eastern Towers | CO-S1-34710 | Lower tower anti graffiti painting - Tower 1 East | 46189 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 60 and above | Y | 46193 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 2 - Superstructure - Edge Girders | 1 - Eastern Towers | CO-S1-34720 | Lower tower anti graffiti painting - Tower 2 East | 46205 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 60 and above | Y | 46209 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 2 - Superstructure - Edge Girders | 1 - Eastern Towers | CO-S1-34780 | Tower Lights Installation - Tower 1 East | 46181 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 0-30 | Y | 46186 | Not Started | Critical | 0-10 | 0-10
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 2 - Superstructure - Edge Girders | 1 - Eastern Towers | CO-S1-34800 | Tower Lights Installation - Tower 2 East | 46197 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | Y | 46202 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 4 - Road Commissioning | 1 - Electrical Commissioning | CO-S1-35080 | Factory Acceptance Testing (FAT) | 46269 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 60 and above | Y | 46269 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 4 - Road Commissioning | 1 - Electrical Commissioning | CO-S1-35090 | Installation Acceptance Testing (IAT) | 46272 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 60 and above | Y | 46300 | Not Started | Not Critical | 10-20 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 4 - Road Commissioning | 1 - Electrical Commissioning | CO-S1-35100 | Site Acceptance Testing (SAT / Energistation of boards) | 46353 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 0-30 | Y | 46366 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 4 - Road Commissioning | 1 - Electrical Commissioning | CO-S1-35110 | Network Integration Testing (NIT) | 46367 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 0-30 | Y | 46370 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 4 - Road Commissioning | 1 - Electrical Commissioning | CO-S1-35120 | Site Integration Acceptance Testing (SIAT) | 46371 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 0-30 | Y | 46405 | Not Started | Not Critical | 10-20 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 4 - Road Commissioning | 1 - Electrical Commissioning | CO-S1-35130 | Pre Installation Testing (PIT) | 46167 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 30-60 | 60 and above | Y | 46212 | Not Started | Not Critical | 20 and Over | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 4 - Road Commissioning | 1 - Electrical Commissioning | CO-S1-35140 | Installation Acceptance Testing (IAT) | 46213 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 60 and above | Y | 46240 | Not Started | Not Critical | 10-20 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 4 - Road Commissioning | 1 - Electrical Commissioning | CO-S1-35150 | Site Acceptance Testing (SAT / Energistation of boards) | 46331 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 0-30 | Y | 46344 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 4 - Road Commissioning | 1 - Electrical Commissioning | CO-S1-35160 | Network Integration Testing (NIT) | 46345 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 0-30 | Y | 46346 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 4 - Road Commissioning | 1 - Electrical Commissioning | CO-S1-35170 | Site Integration Acceptance Testing (SIAT) | 46349 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 0-30 | Y | 46367 | Not Started | Not Critical | 10-20 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 4 - Road Commissioning | 1 - Electrical Commissioning | CO-S1-35180 | Factory Acceptance Testing (FAT) | 46269 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 60 and above | Y | 46269 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 4 - Road Commissioning | 1 - Electrical Commissioning | CO-S1-35190 | Final Systems Testing (FST) | 46370 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 0-30 | Y | 46409 | Not Started | Not Critical | 10-20 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 4 - Road Commissioning | 1 - Electrical Commissioning | CO-S1-35200 | Factory Acceptance Testing (FAT) | 46269 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 60 and above | Y | 46269 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 4 - Road Commissioning | 1 - Electrical Commissioning | CO-S1-35210 | Installation Acceptance Testing (IAT) | 46272 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 60 and above | Y | 46273 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 4 - Road Commissioning | 1 - Electrical Commissioning | CO-S1-35220 | Site Acceptance Testing (SAT / Energistation of boards) | 46316 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 60 and above | Y | 46318 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 4 - Road Commissioning | 1 - Electrical Commissioning | CO-S1-35230 | Factory Acceptance Testing (FAT) | 46269 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 60 and above | Y | 46269 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 4 - Road Commissioning | 1 - Electrical Commissioning | CO-S1-35240 | Installation Acceptance Testing (IAT) - Stage 1 | 46272 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 60 and above | Y | 46274 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 4 - Road Commissioning | 1 - Electrical Commissioning | CO-S1-35250 | Site Acceptance Testing (SAT / Energistation of boards) - Stage 1 | 46315 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 60 and above | Y | 46317 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 4 - Road Commissioning | 1 - Electrical Commissioning | CO-S1-35260 | Installation Acceptance Testing (IAT) - Stage 2 | 46318 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 60 and above | Y | 46321 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 4 - Road Commissioning | 1 - Electrical Commissioning | CO-S1-35270 | Site Acceptance Testing (SAT / Energistation of boards) - Stage 2 | 46322 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 60 and above | Y | 46324 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 4 - Substructure - Abutment Central Sections | 1 - South Abutment | CO-S1-13250 | Reinforcement | 46188 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | Y | 46188 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 4 - Substructure - Abutment Central Sections | 1 - South Abutment | CO-S1-13260 | Formwork | 46189 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | Y | 46189 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 4 - Substructure - Abutment Central Sections | 1 - South Abutment | CO-S1-13270 | Pour | 46191 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | Y | 46191 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 4 - Substructure - Abutment Central Sections | 1 - South Abutment | CO-S1-13290 | Curing & Formwork Strip | 46192 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 60 and above | Y | 46195 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 4 - Substructure - Abutment Central Sections | 1 - South Abutment | CO-S1-13460 | Reinforcement | 46192 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | Y | 46192 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 4 - Substructure - Abutment Central Sections | 1 - South Abutment | CO-S1-13470 | Formwork | 46195 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | Y | 46195 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 4 - Substructure - Abutment Central Sections | 1 - South Abutment | CO-S1-13480 | Pour | 46196 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | Y | 46196 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 4 - Substructure - Abutment Central Sections | 1 - South Abutment | CO-S1-13500 | Curing | 46197 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 60 and above | Y | 46198 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 4 - Substructure - Abutment Central Sections | 1 - South Abutment | CO-S1-13650 | Remove Temporary Sheet Piles on SW and SE | 46170 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 60 and above | N | 46172 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 4 - Substructure - Abutment Central Sections | 1 - South Abutment | CO-S1-19470 | Blinding | 46172 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | N | 46172 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 4 - Substructure - Abutment Central Sections | 1 - South Abutment | CO-S1-19550 | Demolition of Existing Intersection | 46178 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 60 and above | N | 46183 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 4 - Substructure - Abutment Central Sections | 1 - South Abutment | CO-S1-22390 | Approach Slab - Blinding | 46232 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 0-30 | N | 46233 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 4 - Substructure - Abutment Central Sections | 1 - South Abutment | CO-S1-22400 | Approach Slab - Place Rebar | 46233 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 0-30 | N | 46239 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 4 - Substructure - Abutment Central Sections | 1 - South Abutment | CO-S1-22410 | Approach Slab - Install Side Formwork | 46239 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 0-30 | N | 46241 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 4 - Substructure - Abutment Central Sections | 1 - South Abutment | CO-S1-22420 | Approach Slab - Pour Slab | 46241 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 0-30 | N | 46242 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 4 - Substructure - Abutment Central Sections | 1 - South Abutment | CO-S1-22430 | Approach Slab - Curing Time | 46242 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | N | 46247 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 4 - Substructure - Abutment Central Sections | 1 - South Abutment | CO-S1-22470 | Back Wall - Install Formwork | 46169 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 0-30 | N | 46171 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 4 - Substructure - Abutment Central Sections | 1 - South Abutment | CO-S1-22480 | Back Wall - Pour | 46171 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 0-30 | N | 46171 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 4 - Substructure - Abutment Central Sections | 1 - South Abutment | CO-S1-22490 | Back Wall - Curing Time | 46172 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | N | 46174 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 4 - Substructure - Abutment Central Sections | 1 - South Abutment | CO-S1-23200 | Strip Formwork | 46167 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 60 and above | Y | 46167 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 4 - Substructure - Abutment Central Sections | 1 - South Abutment | CO-S1-23210 | Back Wall - Strip Formwork | 46175 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 0-30 | N | 46177 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 4 - Substructure - Abutment Central Sections | 1 - South Abutment | CO-S1-23600 | Excavation & Foundation Prep | 46170 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | N | 46171 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 4 - Substructure - Abutment Central Sections | 1 - South Abutment | CO-S1-27040 | Formwork Strip | 46199 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | Y | 46199 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 4 - Substructure - Abutment Central Sections | 1 - South Abutment | CO-S1-27190 | Reinforcement | 46174 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | Y | 46175 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 4 - Substructure - Abutment Central Sections | 1 - South Abutment | CO-S1-27200 | Formwork | 46183 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | Y | 46184 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 4 - Substructure - Abutment Central Sections | 1 - South Abutment | CO-S1-27210 | Pour | 46185 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | Y | 46185 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 4 - Substructure - Abutment Central Sections | 1 - South Abutment | CO-S1-27220 | Curing | 46186 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | Y | 46188 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 4 - Substructure - Abutment Central Sections | 1 - South Abutment | CO-S1-27230 | Formwork Strip | 46189 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | Y | 46189 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 4 - Substructure - Abutment Central Sections | 1 - South Abutment | CO-S1-27240 | Reinforcement | 46191 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | Y | 46192 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 4 - Substructure - Abutment Central Sections | 1 - South Abutment | CO-S1-27250 | Formwork | 46193 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | Y | 46195 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 4 - Substructure - Abutment Central Sections | 1 - South Abutment | CO-S1-27260 | Pour | 46196 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | Y | 46196 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 4 - Substructure - Abutment Central Sections | 1 - South Abutment | CO-S1-27270 | Curing | 46197 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | Y | 46200 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 4 - Substructure - Abutment Central Sections | 1 - South Abutment | CO-S1-27280 | Formwork Strip | 46202 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | Y | 46204 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 4 - Substructure - Abutment Central Sections | 1 - South Abutment | CO-S1-30090 | RW-M9 (50% Adjacent to Staircase) | 46170 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | Y | 46192 | Not Started | Not Critical | 10-20 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 4 - Substructure - Abutment Central Sections | 1 - South Abutment | CO-S1-31390 | SE Staircase Key | 46227 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | Y | 46245 | Not Started | Not Critical | 10-20 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 4 - Substructure - Abutment Central Sections | 1 - South Abutment | CO-S1-31400 | SE Staircase Base Slab | 46247 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | Y | 46263 | Not Started | Not Critical | 10-20 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 4 - Substructure - Abutment Central Sections | 1 - South Abutment | CO-S1-31410 | SE Staircase Upstand Wall | 46265 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 60 and above | Y | 46277 | Not Started | Not Critical | 10-20 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 4 - Substructure - Abutment Central Sections | 1 - South Abutment | CO-S1-31420 | Limestone Terrace Wall A - Under bridge to SW section (Ch. 26 - 94) | 46185 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 30-60 | 60 and above | Y | 46212 | Not Started | Not Critical | 20 and Over | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 4 - Substructure - Abutment Central Sections | 1 - South Abutment | CO-S1-31430 | Limestone Terrace Wall B - Under bridge to SW section (Ch. 26 - 94) | 46223 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | Y | 46255 | Not Started | Not Critical | 20 and Over | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 4 - Substructure - Abutment Central Sections | 1 - South Abutment | CO-S1-31440 | Limestone Terrace Wall C - Under bridge to SW section (Ch. 26 - 94) | 46256 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | Y | 46293 | Not Started | Not Critical | 20 and Over | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 4 - Substructure - Abutment Central Sections | 1 - South Abutment | CO-S1-31450 | Limestone Terrace Wall D | 46193 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | Y | 46225 | Not Started | Not Critical | 20 and Over | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 4 - Substructure - Abutment Central Sections | 1 - South Abutment | CO-S1-31950 | Structural Backfill SE backwall-RW-M6 & Remove Temporary Piles | 46199 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | Y | 46209 | Not Started | Not Critical | 10-20 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 4 - Substructure - Abutment Central Sections | 1 - South Abutment | CO-S1-31960 | Drainage Install (pit & pipe)- Eastern section | 46209 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | Y | 46221 | Not Started | Not Critical | 10-20 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 4 - Substructure - Abutment Central Sections | 1 - South Abutment | CO-S1-32120 | SE Staircase Backfill Batter | 46279 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 60 and above | Y | 46282 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 4 - Substructure - Abutment Central Sections | 1 - South Abutment | CO-S1-32130 | Construct SE Footpath | 46283 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 60 and above | Y | 46295 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 4 - Substructure - Abutment Central Sections | 1 - South Abutment | CO-S1-32160 | Install Aluminium Security Screens | 46178 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 60 and above | Y | 46179 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 4 - Substructure - Abutment Central Sections | 1 - South Abutment | CO-S1-33170 | Remove temp sheet piles | 46200 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | Y | 46200 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 4 - Substructure - Abutment Central Sections | 1 - South Abutment | CO-S1-33420 | Back Wall - Air curing before water proof | 46178 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | Y | 46184 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 4 - Substructure - Abutment Central Sections | 1 - South Abutment | CO-S1-33430 | Back Wall - Apply primer & waterproofing | 46185 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | Y | 46186 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 4 - Substructure - Abutment Central Sections | 1 - South Abutment | CO-S1-33740 | Limestone Terrace Wall A, B & C - Install ingrounds and architectual lights | 46274 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | Y | 46293 | Not Started | Not Critical | 10-20 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 4 - Substructure - Abutment Central Sections | 1 - South Abutment | CO-S1-33750 | Limestone Terrace Wall B - Install artwork footing | 46204 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 60 and above | Y | 46209 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 4 - Substructure - Abutment Central Sections | 1 - South Abutment | CO-S1-34940 | Formwork | 46205 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | Y | 46206 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 4 - Substructure - Abutment Central Sections | 1 - South Abutment | CO-S1-34950 | Pour | 46207 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | Y | 46207 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 4 - Substructure - Abutment Central Sections | 1 - South Abutment | CO-S1-34960 | Curing | 46208 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | Y | 46210 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 4 - Substructure - Abutment Central Sections | 1 - South Abutment | CO-S1-34970 | Formwork Strip | 46211 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | Y | 46212 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 4 - Substructure - Abutment Central Sections | 1 - South Abutment | CO-S1-34980 | Backfill & Install Pit | 46213 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | Y | 46221 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 4 - Substructure - Abutment Central Sections | 1 - South Abutment | CO-S1-35030 | FRP Shear Key - Formwork | 46164 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_Complete | N |  |  | 0-30 |  | Y | 46164 | Completed | Critical | 0-10 | 0-10
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 4 - Substructure - Abutment Central Sections | 1 - South Abutment | CO-S1-35040 | FRP Shear Key - Concrete Pour | 46165 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | Y | 46165 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 4 - Substructure - Abutment Central Sections | 1 - South Abutment | CO-S1-35050 | FRP Shear Key - Concrete Cure | 46167 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | Y | 46169 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 4 - Substructure - Abutment Central Sections | 1 - South Abutment | CO-S1-35070 | FRP Shear Key - Formwork & Walkway strip | 46170 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | Y | 46171 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 4 - Substructure - Abutment Central Sections | 1 - South Abutment | CO-S1-35280 | SWB01677 - Install ingrounds and DB plinth | 46296 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 60 and above | Y | 46301 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 4 - Substructure - Abutment Central Sections | 1 - South Abutment | CO-S1-35290 | SWB01677 - Install and terminate DB | 46302 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 60 and above | Y | 46307 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 4 - Substructure - Abutment Central Sections | 1 - South Abutment | CO-S1-3690 | Structural Backfill central section of backwall to SG | 46188 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 0-30 | N | 46199 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 4 - Substructure - Abutment Central Sections | 1 - South Abutment | CO-S1-4020 | Drainage Install (pit & pipe)- Central section | 46202 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | N | 46213 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 4 - Substructure - Abutment Central Sections | 2 - North Abutment | CO-S1-1200 | Formwork | 46167 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 0-30 | Y | 46167 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 4 - Substructure - Abutment Central Sections | 2 - North Abutment | CO-S1-1210 | Pour | 46168 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 0-30 | Y | 46168 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 4 - Substructure - Abutment Central Sections | 2 - North Abutment | CO-S1-12840 | Formwork | 46169 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 0-30 | Y | 46169 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 4 - Substructure - Abutment Central Sections | 2 - North Abutment | CO-S1-12850 | Pour | 46170 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 0-30 | Y | 46170 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 4 - Substructure - Abutment Central Sections | 2 - North Abutment | CO-S1-12870 | Curing | 46171 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | Y | 46173 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 4 - Substructure - Abutment Central Sections | 2 - North Abutment | CO-S1-22360 | Approach Slab - Strip Formwork | 46223 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 0-30 | N | 46223 | Not Started | Not Critical | 0-10 | 10-20
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 4 - Substructure - Abutment Central Sections | 2 - North Abutment | CO-S1-22370 | Approach Slab - Pour Slab | 46216 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 0-30 | N | 46216 | Not Started | Not Critical | 0-10 | 10-20
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 4 - Substructure - Abutment Central Sections | 2 - North Abutment | CO-S1-22380 | Approach Slab - Curing Time | 46217 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 0-30 | N | 46221 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 4 - Substructure - Abutment Central Sections | 2 - North Abutment | CO-S1-26810 | Strip Formwork | 46175 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 0-30 | Y | 46175 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 4 - Substructure - Abutment Central Sections | 2 - North Abutment | CO-S1-26850 | Strip Formwork | 46175 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 0-30 | Y | 46175 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 4 - Substructure - Abutment Central Sections | 2 - North Abutment | CO-S1-31520 | Earthworks to Revetment Profile | 46168 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | Y | 46172 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 4 - Substructure - Abutment Central Sections | 2 - North Abutment | CO-S1-31530 | Revetment and Backfill | 46174 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | Y | 46206 | Not Started | Not Critical | 20 and Over | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 4 - Substructure - Abutment Central Sections | 2 - North Abutment | CO-S1-31540 | RW-M1 & M2 Base Slab | 46211 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 0-30 | Y | 46221 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 4 - Substructure - Abutment Central Sections | 2 - North Abutment | CO-S1-31550 | Northwest Stairs to 3rd Landing | 46231 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 60 and above | Y | 46245 | Not Started | Not Critical | 10-20 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 4 - Substructure - Abutment Central Sections | 2 - North Abutment | CO-S1-31560 | RW-M1 & M2 Walls | 46223 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 0-30 | Y | 46241 | Not Started | Not Critical | 10-20 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 4 - Substructure - Abutment Central Sections | 2 - North Abutment | CO-S1-31570 | Backfill Inside of RW-M1 & RW-M2 to Underside of PSP Subbase | 46242 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 60 and above | Y | 46248 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 4 - Substructure - Abutment Central Sections | 2 - North Abutment | CO-S1-31580 | Northwest Stairs to Top Landing | 46249 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 60 and above | Y | 46262 | Not Started | Not Critical | 10-20 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 4 - Substructure - Abutment Central Sections | 2 - North Abutment | CO-S1-31720 | Jetty Abutment Demolition | 46283 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 0-30 | Y | 46291 | Not Started | Critical | 0-10 | 0-10
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 4 - Substructure - Abutment Central Sections | 2 - North Abutment | CO-S1-31730 | Removal of Adjacent Structures | 46293 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 0-30 | Y | 46297 | Not Started | Critical | 0-10 | 0-10
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 4 - Substructure - Abutment Central Sections | 2 - North Abutment | CO-S1-31740 | Revetment and Backfill | 46297 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 0-30 | Y | 46311 | Not Started | Critical | 10-20 | 0-10
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 4 - Substructure - Abutment Central Sections | 2 - North Abutment | CO-S1-31750 | RW-M4 Base Slab | 46311 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 0-30 | Y | 46324 | Not Started | Critical | 10-20 | 0-10
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 4 - Substructure - Abutment Central Sections | 2 - North Abutment | CO-S1-31760 | Northeast Stairs to 2nd Landing | 46345 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 0-30 | Y | 46356 | Not Started | Critical | 0-10 | 0-10
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 4 - Substructure - Abutment Central Sections | 2 - North Abutment | CO-S1-31770 | RW-M4 Walls & Parapets | 46324 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 0-30 | Y | 46345 | Not Started | Critical | 10-20 | 0-10
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 4 - Substructure - Abutment Central Sections | 2 - North Abutment | CO-S1-31790 | Northeast Stairs to Top Landing | 46356 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 0-30 | Y | 46363 | Not Started | Critical | 0-10 | 0-10
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 4 - Substructure - Abutment Central Sections | 2 - North Abutment | CO-S1-32170 | Install Aluminium Security Screens | 46181 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 60 and above | Y | 46182 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 4 - Substructure - Abutment Central Sections | 2 - North Abutment | CO-S1-3390 | Curing | 46169 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | Y | 46171 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 4 - Substructure - Abutment Central Sections | 2 - North Abutment | CO-S1-34920 | RW-M3 Base Slab | 46191 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 0-30 | Y | 46195 | Not Started | Not Critical | 0-10 | 10-20
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 4 - Substructure - Abutment Central Sections | 2 - North Abutment | CO-S1-34930 | RW-M3 Wall (Incl. curing & strip) | 46196 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 0-30 | Y | 46205 | Not Started | Not Critical | 0-10 | 10-20
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 4 - Substructure - Abutment Central Sections | 2 - North Abutment | CO-S1-4360 | Approach Slab - Foundation Preparation & Blinding | 46203 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 0-30 | N | 46206 | Not Started | Not Critical | 0-10 | 10-20
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 4 - Substructure - Abutment Central Sections | 2 - North Abutment | CO-S1-4370 | Approach Slab - Place Rebar | 46207 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 0-30 | N | 46212 | Not Started | Not Critical | 0-10 | 10-20
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 4 - Substructure - Abutment Central Sections | 2 - North Abutment | CO-S1-4380 | Approach Slab - Install Side Formwork | 46213 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 0-30 | N | 46214 | Not Started | Not Critical | 0-10 | 10-20
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 1 - On-Bridge Road Works | 2 - Road Carriageway | CO-S1-23350 | Road Carriageway - Bituminous Surfacing & Waterproofing | 46251 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | N | 46258 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 1 - On-Bridge Road Works | 2 - Road Carriageway | CO-S1-23370 | Road Carriageway - Kerb Install | 46259 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | N | 46266 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 1 - On-Bridge Road Works | 2 - Road Carriageway | CO-S1-23380 | Road Carriageway - Median Concrete Infills | 46267 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | N | 46272 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 1 - On-Bridge Road Works | 2 - Road Carriageway | CO-S1-23390 | Road Carriageway - Asphalt Surfacing | 46273 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | N | 46279 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 1 - On-Bridge Road Works | 2 - Road Carriageway | CO-S1-23400 | Road Carriageway - Linemarking | 46280 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | N | 46283 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 1 - On-Bridge Road Works | 2 - Road Carriageway | CO-S1-32100 | Install Saw Tooth Expansion Joints and Concrete Upstands (Ready to Cross New Bridge) | 46284 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | Y | 46294 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 1 - On-Bridge Road Works | 2 - Road Carriageway | CO-S1-32180 | Install Texas Metalwork Barrier | 46280 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | Y | 46293 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 1 - On-Bridge Road Works | 2 - Road Carriageway | CO-S1-32450 | Install bench street lighting pole | 46249 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N | CS_ALAP |  | 0-30 | 30-60 | Y | 46250 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 1 - On-Bridge Road Works | 2 - Road Carriageway | CO-S1-33950 | Road Carriageway - Signage installation | 46284 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | Y | 46287 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 2 - Superstructure - Edge Girders | 2 - Western Towers | CO-S1-24510 | Removal of Scaffold Access - Tower 2 West | 46197 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 60 and above | Y | 46204 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 2 - Superstructure - Edge Girders | 2 - Western Towers | CO-S1-24520 | Removal of Scaffold Access - Tower 1 West | 46192 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | Y | 46200 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 2 - Superstructure - Edge Girders | 2 - Western Towers | CO-S1-34690 | Lower tower anti graffiti painting - Tower 1 West | 46196 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 60 and above | Y | 46200 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 2 - Superstructure - Edge Girders | 2 - Western Towers | CO-S1-34700 | Lower tower anti graffiti painting - Tower 2 West | 46200 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 60 and above | Y | 46204 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 2 - Superstructure - Edge Girders | 2 - Western Towers | CO-S1-34770 | Tower Lights Installation - Tower 1 West | 46186 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | Y | 46192 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 2 - Superstructure - Edge Girders | 2 - Western Towers | CO-S1-34790 | Tower Lights Installation - Tower 2 West | 46192 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | Y | 46197 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 1 - On-Bridge Road Works | 3 - Principal Shared Path | CO-S1-23440 | PSP/SUP - Seal | 46277 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | N | 46279 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 1 - On-Bridge Road Works | 3 - Principal Shared Path | CO-S1-23450 | PSP/SUP - Corrector Layer | 46280 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | N | 46284 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 1 - On-Bridge Road Works | 3 - Principal Shared Path | CO-S1-23460 | PSP/SUP - Dense Grade Asphalt | 46297 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 0-30 | N | 46307 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 1 - On-Bridge Road Works | 3 - Principal Shared Path | CO-S1-23470 | PSP/SUP - Linemarking | 46308 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | N | 46310 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 4 - Substructure - Abutment Central Sections | 3 - Scour Protection - Remaining Works | CO-S1-33160 | Install Remaining Scour Protection at Northern Towers | 46283 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | Y | 46310 | Not Started | Not Critical | 20 and Over | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 2 - Superstructure - Edge Girders | 3 - Stay Cable Retensioning | CO-S1-25770 | Stay Restressing Stage 4 - Cable Stays 6-7 | 46203 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 0-30 | Y | 46204 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 2 - Superstructure - Edge Girders | 3 - Stay Cable Retensioning | CO-S1-26690 | Stay Restressing Stage 5 - CS8 | 46239 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | Y | 46240 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 1 - On-Bridge Road Works | 4 - Bridge Finishes | CO-S1-23480 | Install Anti-Graffiti Coating on Accessible Areas | 46262 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | N | 46273 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 1 - On-Bridge Road Works | 4 - Bridge Finishes | CO-S1-23490 | Street and Architectural Lighting | 46270 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | N | 46294 | Not Started | Not Critical | 10-20 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 1 - On-Bridge Road Works | 4 - Bridge Finishes | CO-S1-23500 | Street Furniture (Benches & Lighting Column Shrouds) | 46284 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 0-30 | N | 46296 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 1 - On-Bridge Road Works | 4 - Bridge Finishes | CO-S1-35350 | On bridge Orb lighting at towers | 46247 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 60 and above | Y | 46253 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 1 - On-Bridge Road Works | 4 - Bridge Finishes | CO-S1-35500 | On bridge street Lighting | 46280 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | Y | 46291 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 3 - Superstructure - Demolition and Deck Install | 4 - Installation of Transverse Beams | CO-S1-23840 | Install A2-23S (Diaphragm) | 46178 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | N | 46178 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 3 - Superstructure - Demolition and Deck Install | 4 - Installation of Transverse Beams | CO-S1-24100 | Install A2-21S | 46178 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | N | 46178 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 3 - Superstructure - Demolition and Deck Install | 4 - Installation of Transverse Beams | CO-S1-32280 | Remove Scaffold Access T1-19S | 46165 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | Y | 46165 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 2 - Superstructure - Edge Girders | 4 - Temporary PT Deconstruction | CO-S1-33690 | Install conduits/containment in girders West | 46183 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 60 and above | Y | 46207 | Not Started | Not Critical | 10-20 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 2 - Superstructure - Edge Girders | 4 - Temporary PT Deconstruction | CO-S1-35510 | Install conduits/containment in Galleries | 46183 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 60 and above | Y | 46207 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 2 - Superstructure - Edge Girders | 5 - Finishing Works | CO-S1-25780 | Final lift - off | 46308 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 0-30 | Y | 46314 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 2 - Superstructure - Edge Girders | 5 - Finishing Works | CO-S1-25790 | Strand trimming, protection cap installation and vacuum test | 46315 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 0-30 | Y | 46325 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 2 - Superstructure - Edge Girders | 5 - Finishing Works | CO-S1-25800 | Resin injection for anchorage (inside box) | 46326 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 0-30 | Y | 46331 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 2 - Superstructure - Edge Girders | 5 - Finishing Works | CO-S1-25820 | Guide deviator installation and closing of Anti-Vandal Pipe | 46332 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 0-30 | Y | 46337 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 2 - Superstructure - Edge Girders | 5 - Finishing Works | CO-S1-26710 | Installation of Collar around Stays on Top Deck | 46338 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 0-30 | Y | 46343 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 1 - On-Bridge Road Works | 5 - Parapet & Balustrade | CO-S1-23410 | Install Parapet NE - T1 to Abutment (21 No. units) | 46169 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 60 and above | N | 46175 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 1 - On-Bridge Road Works | 5 - Parapet & Balustrade | CO-S1-23420 | Install Balustrade NE - T1 to Abutment | 46267 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | N | 46276 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 1 - On-Bridge Road Works | 5 - Parapet & Balustrade | CO-S1-26740 | Prefabrication of 4x Hung Scaffold | 46205 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | Y | 46214 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 1 - On-Bridge Road Works | 5 - Parapet & Balustrade | CO-S1-26750 | Prefabrication of 4x Tower Hung Scaffold | 46172 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 60 and above | Y | 46191 | Not Started | Not Critical | 10-20 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 1 - On-Bridge Road Works | 5 - Parapet & Balustrade | CO-S1-26760 | Install Parapet Lighting | 46219 | CP_Phys | TT_LOE | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  |  |  | Y | 46248 | Not Started | Not Critical | 20 and Over | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 1 - On-Bridge Road Works | 5 - Parapet & Balustrade | CO-S1-33510 | Install Waterproofing along parapet edge | 46270 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N | CS_ALAP |  | 0-30 | 30-60 | Y | 46276 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 1 - On-Bridge Road Works | 5 - Parapet & Balustrade | CO-S1-33670 | Install parapet lighting access | 46212 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N | CS_ALAP |  | 0-30 | 30-60 | Y | 46217 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 1 - On-Bridge Road Works | 5 - Parapet & Balustrade | CO-S1-33980 | Install Parapet Eastern side - (22 No. units) | 46216 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | Y | 46223 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 1 - On-Bridge Road Works | 5 - Parapet & Balustrade | CO-S1-34280 | Install Balustrade W Midspan - T2 to T1 inclusive | 46211 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | Y | 46220 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 1 - On-Bridge Road Works | 5 - Parapet & Balustrade | CO-S1-34290 | Install Balustrade NW - T1 to Abutment | 46221 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | Y | 46231 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 1 - On-Bridge Road Works | 5 - Parapet & Balustrade | CO-S1-34300 | Install Balustrade SW - T2 to Abutment | 46232 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | Y | 46242 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 1 - On-Bridge Road Works | 5 - Parapet & Balustrade | CO-S1-34310 | Install Balustrade E Midspan - T2 to T1 inclusive | 46244 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | Y | 46253 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 1 - On-Bridge Road Works | 5 - Parapet & Balustrade | CO-S1-34320 | Install Balustrade SE - T2 to Abutment | 46255 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | Y | 46263 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 1 - On-Bridge Road Works | 5 - Parapet & Balustrade | CO-S1-34480 | Install Parapet North Backspan (10 No. units) | 46224 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | Y | 46230 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 1 - On-Bridge Road Works | 5 - Parapet & Balustrade | CO-S1-34490 | Install Parapet South Backspan (13 No. units) | 46200 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 60 and above | Y | 46205 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 1 - On-Bridge Road Works | 5 - Parapet & Balustrade | CO-S1-35300 | Install Parapet SW | 46197 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 60 and above | Y | 46204 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 1 - On-Bridge Road Works | 5 - Parapet & Balustrade | CO-S1-35360 | Install Parapet Lighting - NW & W Nav channel - groups 1 to 6 (152 No. lights) | 46219 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | Y | 46239 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 1 - On-Bridge Road Works | 5 - Parapet & Balustrade | CO-S1-35370 | Install Parapet Lighting - SW - groups 7 to 9 (161 No. lights) | 46240 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | Y | 46248 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 1 - On-Bridge Road Works | 5 - Parapet & Balustrade | CO-S1-35380 | Install Parapet Lighting - NE - groups 1 to 3 (74 No. lights) | 46219 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | Y | 46225 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 1 - On-Bridge Road Works | 5 - Parapet & Balustrade | CO-S1-35390 | Install Parapet Lighting - E Nav channel - groups 4 & 5 (63 No. lights) | 46227 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | Y | 46231 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 1 - On-Bridge Road Works | 5 - Parapet & Balustrade | CO-S1-35400 | Install Parapet Lighting - SE - group 6 (13 No. lights) | 46232 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | Y | 46233 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 1 - On-Bridge Road Works | 5 - Parapet & Balustrade | CO-S1-35410 | Install Parapet Lighting - SE - groups 7 to 9 (165 No. lights) | 46235 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | Y | 46242 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 1 - On-Bridge Road Works | 5 - Parapet & Balustrade | CO-S1-35420 | Install & terminate Parapet Lighting Cabinets for parapet groups 1 to 9 - East girder | 46265 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 0-30 | Y | 46275 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 1 - On-Bridge Road Works | 5 - Parapet & Balustrade | CO-S1-35430 | Install & terminate Parapet Lighting Cabinets for parapet groups 1 to 9 - West girder | 46276 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 0-30 | Y | 46288 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 1 - On-Bridge Road Works | 5 - Parapet & Balustrade | CO-S1-35440 | Install handrail lights W T2 to T1 inclusive | 46223 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 60 and above | Y | 46230 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 1 - On-Bridge Road Works | 5 - Parapet & Balustrade | CO-S1-35450 | Install handrail lights East midspan | 46260 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 60 and above | Y | 46266 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 1 - On-Bridge Road Works | 5 - Parapet & Balustrade | CO-S1-35460 | Install handrail lights - T2 to SW Abutment | 46244 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 60 and above | Y | 46251 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 1 - On-Bridge Road Works | 5 - Parapet & Balustrade | CO-S1-35470 | Install handrail lights NW Abutment to T1 | 46252 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 60 and above | Y | 46259 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 1 - On-Bridge Road Works | 5 - Parapet & Balustrade | CO-S1-35480 | Install handrail lights T2 to SE Abutment | 46267 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 60 and above | Y | 46274 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 1 - On-Bridge Road Works | 5 - Parapet & Balustrade | CO-S1-35490 | Install handrail lights NE abutment to T1 | 46279 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 60 and above | Y | 46286 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 3 - Superstructure - Demolition and Deck Install | 5 - Transverse Beams Stitches | CO-S1-25830 | Install A2-21S Stitches (All Works) | 46179 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | Y | 46185 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 3 - Superstructure - Demolition and Deck Install | 5 - Transverse Beams Stitches | CO-S1-25940 | Install A1-21N & 22N (Diaphragm) Stitches (Pour & Stress) | 46164 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_Active | N |  |  | 0-30 | 0-30 | Y | 46165 | In Progress | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 3 - Superstructure - Demolition and Deck Install | 5 - Transverse Beams Stitches | CO-S1-25950 | Install A2-23S (Diaphragm) Stitches (All Works) | 46179 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | Y | 46185 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 3 - Superstructure - Demolition and Deck Install | 5 - Transverse Beams Stitches | CO-S1-34600 | Install A1-21N & 22N (Diaphragm) Stitches (Grout & Condeck) | 46167 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | Y | 46171 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 3 - Superstructure - Demolition and Deck Install | 6 - Installation of Permadec Panels | CO-S1-26230 | Install A2-20S | 46172 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | Y | 46174 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 3 - Superstructure - Demolition and Deck Install | 6 - Installation of Permadec Panels | CO-S1-26310 | Install T2-12S | 46165 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | Y | 46167 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 3 - Superstructure - Demolition and Deck Install | 6 - Installation of Permadec Panels | CO-S1-26350 | Install A2-22S | 46186 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | Y | 46188 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 3 - Superstructure - Demolition and Deck Install | 6 - Installation of Permadec Panels | CO-S1-26360 | Install T2-16N | 46164 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_Complete | N |  |  | 0-30 |  | Y | 46164 | Completed | Critical | 0-10 | 0-10
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 3 - Superstructure - Demolition and Deck Install | 6 - Installation of Permadec Panels | CO-S1-26380 | Install T2-18N | 46172 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | Y | 46174 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 3 - Superstructure - Demolition and Deck Install | 6 - Installation of Permadec Panels | CO-S1-26390 | Install T2-18S | 46164 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_Complete | N |  |  | 0-30 |  | Y | 46164 | Completed | Critical | 0-10 | 0-10
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 3 - Superstructure - Demolition and Deck Install | 6 - Installation of Permadec Panels | CO-S1-26580 | Install A1-20N | 46164 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_Complete | N |  |  | 0-30 |  | Y | 46164 | Completed | Critical | 0-10 | 0-10
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 3 - Superstructure - Demolition and Deck Install | 6 - Installation of Permadec Panels | CO-S1-26630 | Install Mid Span Permadec Panels | 46164 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_Complete | N |  |  | 0-30 |  | Y | 46164 | Completed | Critical | 0-10 | 0-10
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 2 - North of River - Road Works | 6 - North of River - Road Works for OFT | CO-S1-19700 | Base Course place & compact Ch 160-350 (North of Approach Slab) | 46237 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | Y |  | Yes | 0-30 | 0-30 | Y | 46242 | Not Started | Critical | 0-10 | 0-10
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 2 - North of River - Road Works | 6 - North of River - Road Works for OFT | CO-S1-19760 | QVS - Transition Barrier FRP | 46276 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | Y |  | Yes | 0-30 | 0-30 | N | 46293 | Not Started | Critical | 10-20 | 0-10
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 2 - North of River - Road Works | 6 - North of River - Road Works for OFT | CO-S1-19770 | QVS - Asphalt | 46296 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | Y |  | Yes | 0-30 | 0-30 | N | 46300 | Not Started | Critical | 0-10 | 0-10
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 2 - North of River - Road Works | 6 - North of River - Road Works for OFT | CO-S1-19820 | QVS - Line Marking & Signage (Ready to Cross New Bridge) | 46301 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | Y |  | Yes | 30-60 | 0-30 | N | 46339 | Not Started | Critical | 20 and Over | 0-10
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 2 - North of River - Road Works | 6 - North of River - Road Works for OFT | CO-S1-31500 | QVS - Installation of Thrie Beam & Terminal | 46294 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | Y |  | Yes | 0-30 | 0-30 | Y | 46295 | Not Started | Critical | 0-10 | 0-10
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 2 - North of River - Road Works | 6 - North of River - Road Works for OFT | CO-S1-31970 | QVS - Balustrade Handrail Install | 46242 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | Y | 46247 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 2 - North of River - Road Works | 6 - North of River - Road Works for OFT | CO-S1-33640 | Drainage N section Ch 160-350 (All remaining) | 46191 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | Y |  | Yes | 0-30 | 0-30 | Y | 46202 | Not Started | Critical | 0-10 | 0-10
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 2 - North of River - Road Works | 6 - North of River - Road Works for OFT | CO-S1-33650 | Drainage N section Ch 350-380 (NEa-0 to NWa-0) | 46175 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 0-30 | Y | 46179 | Not Started | Not Critical | 0-10 | 10-20
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 2 - North of River - Road Works | 6 - North of River - Road Works for OFT | CO-S1-33660 | Services crossing Ch 350-380 & Precast pit install | 46212 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 0-30 | Y | 46217 | Not Started | Critical | 0-10 | 0-10
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 2 - North of River - Road Works | 6 - North of River - Road Works for OFT | CO-S1-34460 | Terra mesh installation - North East Ch 240-350 - Stage 1 | 46172 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | Y |  | Yes | 0-30 | 0-30 | Y | 46189 | Not Started | Critical | 10-20 | 0-10
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 2 - North of River - Road Works | 6 - North of River - Road Works for OFT | CO-S1-34860 | Subgrade & Subbase Ch 160-350 (North of Approach Slab) | 46227 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | Y |  | Yes | 0-30 | 0-30 | Y | 46235 | Not Started | Critical | 0-10 | 0-10
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 2 - North of River - Road Works | 6 - North of River - Road Works for OFT | CO-S1-34880 | Terra mesh installation & final backfill to subgrade - North East Ch 240-350 - Stage 2 | 46203 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | Y |  | Yes | 0-30 | 0-30 | Y | 46225 | Not Started | Critical | 10-20 | 0-10
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 2 - North of River - Road Works | 6 - North of River - Road Works for OFT | CO-S1-34910 | Bulk Earthworks Ch 160-350 (North of Approach Slab) | 46164 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_Active | N |  |  | 0-30 | 0-30 | Y | 46185 | In Progress | Critical | 10-20 | 0-10
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 2 - North of River - Road Works | 6 - North of River - Road Works for OFT | CO-S1-35320 | Services NE connection to bridge | 46206 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 60 and above | Y | 46212 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 2 - North of River - Road Works | 6 - North of River - Road Works for OFT | CO-S1-35330 | Install SWB 01680 & 0900 and terminate | 46270 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 60 and above | Y | 46284 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 2 - North of River - Road Works | 6 - North of River - Road Works for OFT | CO-S1-35340 | Services NW Irrigation connection Podger Lane to L3-BR | 46165 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 60 and above | Y | 46170 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 2 - North of River - Road Works | 6 - North of River - Road Works for OFT | CO-S1-4290 | Bulk Earthworks Ch 350-380 (Approach Slab) | 46165 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 0-30 | N | 46174 | Not Started | Not Critical | 0-10 | 10-20
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 2 - North of River - Road Works | 6 - North of River - Road Works for OFT | CO-S1-4320 | Subgrade & Subbase Ch 350-380 (Approach Slab) | 46186 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 0-30 | N | 46202 | Not Started | Not Critical | 10-20 | 10-20
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 2 - North of River - Road Works | 6 - North of River - Road Works for OFT | CO-S1-6575 | QVS - Base Course, Final Trim & Dryback | 46244 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | Y |  | Yes | 0-30 | 0-30 | N | 46249 | Not Started | Critical | 0-10 | 0-10
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 2 - North of River - Road Works | 6 - North of River - Road Works for OFT | CO-S1-6585 | QVS - Prime Coat & Seal | 46251 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | Y |  | Yes | 0-30 | 0-30 | N | 46261 | Not Started | Critical | 0-10 | 0-10
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 2 - North of River - Road Works | 6 - North of River - Road Works for OFT | CO-S1-6595 | QVS - Median Kerbing | 46267 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | Y |  | Yes | 0-30 | 0-30 | N | 46272 | Not Started | Critical | 0-10 | 0-10
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 2 - North of River - Road Works | 6 - North of River - Road Works for OFT | CO-S1-6605 | QVS - TL4 Slipform Barrier Install | 46267 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | Y |  | Yes | 0-30 | 0-30 | N | 46275 | Not Started | Critical | 0-10 | 0-10
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 2 - North of River - Road Works | 6 - North of River - Road Works for OFT | CO-S1-6615 | QVS - Median Concrete Infill | 46273 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 0-30 | N | 46274 | Not Started | Critical | 0-10 | 0-10
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 2 - North of River - Road Works | 6 - North of River - Road Works for OFT | CO-S1-6995 | QVS - Raise & set drainage pits | 46262 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | Y |  | Yes | 0-30 | 0-30 | N | 46266 | Not Started | Critical | 0-10 | 0-10
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 3 - South of River - Road Works | 6 - South of River - Road Works for OFT | CO-S1-19580 | Subgrade | 46200 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | N | 46204 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 3 - South of River - Road Works | 6 - South of River - Road Works for OFT | CO-S1-19590 | Subbase & Base Course | 46221 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 0-30 | N | 46232 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 3 - South of River - Road Works | 6 - South of River - Road Works for OFT | CO-S1-19600 | Prime | 46248 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 0-30 | N | 46252 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 3 - South of River - Road Works | 6 - South of River - Road Works for OFT | CO-S1-19610 | Set Pit Lids | 46258 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 0-30 | N | 46262 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 3 - South of River - Road Works | 6 - South of River - Road Works for OFT | CO-S1-19620 | Seal | 46254 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 0-30 | N | 46256 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 3 - South of River - Road Works | 6 - South of River - Road Works for OFT | CO-S1-19630 | Kerbs and Medians | 46263 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 0-30 | N | 46269 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 3 - South of River - Road Works | 6 - South of River - Road Works for OFT | CO-S1-19640 | Island Infill | 46270 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 0-30 | N | 46275 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 3 - South of River - Road Works | 6 - South of River - Road Works for OFT | CO-S1-19650 | Asphalt Dense Grade | 46276 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 0-30 | N | 46277 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 3 - South of River - Road Works | 6 - South of River - Road Works for OFT | CO-S1-19660 | Line Marking & Signage | 46279 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 0-30 | N | 46307 | Not Started | Not Critical | 20 and Over | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 3 - South of River - Road Works | 6 - South of River - Road Works for OFT | CO-S1-19670 | Work Complete & Ready to Cross New Bridge) | 46307 | CP_Phys | TT_FinMile | DT_FixedDrtn | RV_OK | TK_NotStart | N |  |  | 0-30 | 0-30 | N | 46307 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 3 - South of River - Road Works | 6 - South of River - Road Works for OFT | CO-S1-31940 | Electrical & ITS - Install Pits & Conduits, Footings & plinths | 46212 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | Y | 46228 | Not Started | Not Critical | 10-20 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 3 - South of River - Road Works | 6 - South of River - Road Works for OFT | CO-S1-32110 | Install Concrete Barriers | 46232 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | Y | 46252 | Not Started | Not Critical | 10-20 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 3 - South of River - Road Works | 6 - South of River - Road Works for OFT | CO-S1-33710 | Electrical & ITS - Install SWB 01677, Poles, CCTV & Traffic signals | 46270 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | Y | 46283 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 3 - South of River - Road Works | 6 - South of River - Road Works for OFT | CO-S1-33940 | Install Energy absorbing bollards | 46252 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | Y | 46260 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 3 - Superstructure - Demolition and Deck Install | 7 - FRP Bridge Deck | CO-S1-24170 | Deck FRP Pour 3 - Place Rebar | 46205 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | N | 46224 | Not Started | Not Critical | 10-20 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 3 - Superstructure - Demolition and Deck Install | 7 - FRP Bridge Deck | CO-S1-24180 | Deck FRP Pour 3 - Install Deck Formwork | 46225 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | N | 46227 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 3 - Superstructure - Demolition and Deck Install | 7 - FRP Bridge Deck | CO-S1-24190 | Deck FRP Pour 3 - Pour In-situ Deck Slab | 46228 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | N | 46228 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 3 - Superstructure - Demolition and Deck Install | 7 - FRP Bridge Deck | CO-S1-24200 | Deck FRP Pour 3 - Curing Time | 46229 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | N | 46235 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 3 - Superstructure - Demolition and Deck Install | 7 - FRP Bridge Deck | CO-S1-24220 | Deck FRP Pour 5 - Place Rebar | 46205 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | N | 46219 | Not Started | Not Critical | 10-20 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 3 - Superstructure - Demolition and Deck Install | 7 - FRP Bridge Deck | CO-S1-24230 | Deck FRP Pour 5 - Install Deck Formwork | 46220 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | N | 46221 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 3 - Superstructure - Demolition and Deck Install | 7 - FRP Bridge Deck | CO-S1-24240 | Final Bridge Deck Pour Complete | 46237 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | N | 46237 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 3 - Superstructure - Demolition and Deck Install | 7 - FRP Bridge Deck | CO-S1-24250 | Deck FRP Pour 5 - Curing Time | 46238 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | N | 46244 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 3 - Superstructure - Demolition and Deck Install | 7 - FRP Bridge Deck | CO-S1-24270 | Deck FRP Pour 4 - Place Rebar | 46184 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | N | 46202 | Not Started | Not Critical | 10-20 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 3 - Superstructure - Demolition and Deck Install | 7 - FRP Bridge Deck | CO-S1-24280 | Deck FRP Pour 4 - Install Deck Formwork | 46205 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | N | 46206 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 3 - Superstructure - Demolition and Deck Install | 7 - FRP Bridge Deck | CO-S1-24290 | Deck FRP Pour 4 - Pour In-situ Deck Slab | 46207 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | N | 46207 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 3 - Superstructure - Demolition and Deck Install | 7 - FRP Bridge Deck | CO-S1-24300 | Deck FRP Pour 4 - Curing Time | 46208 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 60 and above | N | 46214 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 3 - Superstructure - Demolition and Deck Install | 7 - FRP Bridge Deck | CO-S1-31140 | Deck FRP Pour 1B - Install Side Forms | 46172 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | Y | 46174 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 3 - Superstructure - Demolition and Deck Install | 7 - FRP Bridge Deck | CO-S1-31150 | Deck FRP Pour 1B - Pour In-situ Deck Slab | 46175 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | Y | 46175 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 3 - Superstructure - Demolition and Deck Install | 7 - FRP Bridge Deck | CO-S1-31160 | Deck FRP Pour 1B - Curing Time | 46176 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | Y | 46182 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 3 - Superstructure - Demolition and Deck Install | 7 - FRP Bridge Deck | CO-S1-31170 | Deck FRP Pour 1C - Place Rebar | 46172 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | Y | 46186 | Not Started | Not Critical | 10-20 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 3 - Superstructure - Demolition and Deck Install | 7 - FRP Bridge Deck | CO-S1-31180 | Deck FRP Pour 1C - Install Side Forms | 46188 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | Y | 46189 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 3 - Superstructure - Demolition and Deck Install | 7 - FRP Bridge Deck | CO-S1-31190 | Deck FRP Pour 1C - Pour In-situ Deck Slab | 46191 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | Y | 46191 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 3 - Superstructure - Demolition and Deck Install | 7 - FRP Bridge Deck | CO-S1-31200 | Deck FRP Pour 1C - Curing Time | 46192 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | Y | 46198 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 3 - Superstructure - Demolition and Deck Install | 7 - FRP Bridge Deck | CO-S1-31230 | Deck FRP Pour 2B - Pour In-situ Deck Slab | 46164 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_Complete | N |  |  | 0-30 |  | Y | 46164 | Completed | Critical | 0-10 | 0-10
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 3 - Superstructure - Demolition and Deck Install | 7 - FRP Bridge Deck | CO-S1-31240 | Deck FRP Pour 2B - Curing Time | 46165 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 0-30 | Y | 46171 | Not Started | Not Critical | 0-10 | 10-20
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 3 - Superstructure - Demolition and Deck Install | 7 - FRP Bridge Deck | CO-S1-31250 | Deck FRP Pour 2C - Place Rebar | 46165 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 0-30 | Y | 46179 | Not Started | Near Critical | 10-20 | 0-10
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 3 - Superstructure - Demolition and Deck Install | 7 - FRP Bridge Deck | CO-S1-31260 | Deck FRP Pour 2C - Install Deck Formwork | 46181 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 0-30 | Y | 46183 | Not Started | Near Critical | 0-10 | 0-10
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 3 - Superstructure - Demolition and Deck Install | 7 - FRP Bridge Deck | CO-S1-31270 | Deck FRP Pour 2C - Pour In-situ Deck Slab | 46184 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 0-30 | Y | 46184 | Not Started | Near Critical | 0-10 | 0-10
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 3 - Superstructure - Demolition and Deck Install | 7 - FRP Bridge Deck | CO-S1-31280 | Deck FRP Pour 2C - Curing Time | 46185 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | Y | 46191 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 3 - Superstructure - Demolition and Deck Install | 7 - FRP Bridge Deck | CO-S1-32050 | Pour SW Flare | 46169 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | Y | 46169 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 3 - Superstructure - Demolition and Deck Install | 7 - FRP Bridge Deck | CO-S1-32060 | SE & SW Flares - Curing Time | 46172 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 60 and above | Y | 46178 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 3 - Superstructure - Demolition and Deck Install | 7 - FRP Bridge Deck | CO-S1-32090 | Pour SE Flare | 46171 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | Y | 46171 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 3 - Superstructure - Demolition and Deck Install | 7 - FRP Bridge Deck | CO-S1-33440 | Deck FRP Pour 1B - Waterproof segment to deck & 1A CJ | 46183 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 60 and above | Y | 46183 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 3 - Superstructure - Demolition and Deck Install | 7 - FRP Bridge Deck | CO-S1-33450 | Deck FRP Pour 1C - Waterproof segment to deck & 1A CJ | 46199 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | Y | 46199 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 3 - Superstructure - Demolition and Deck Install | 7 - FRP Bridge Deck | CO-S1-33460 | Deck FRP Pour 2B - Waterproof segment to deck & 2A CJ | 46172 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 60 and above | Y | 46172 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 3 - Superstructure - Demolition and Deck Install | 7 - FRP Bridge Deck | CO-S1-33470 | Deck FRP Pour 2C - Waterproof segment to deck & 2A CJ | 46192 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 60 and above | Y | 46192 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 3 - Superstructure - Demolition and Deck Install | 7 - FRP Bridge Deck | CO-S1-33480 | Deck FRP Pour 3 - Waterproof segment to deck & 1C CJ | 46237 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | Y | 46237 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 3 - Superstructure - Demolition and Deck Install | 7 - FRP Bridge Deck | CO-S1-33490 | Deck FRP Pour 4 - Waterproof segment to deck & 2C CJ | 46216 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | Y | 46216 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 1 - Structure Works | 3 - Superstructure - Demolition and Deck Install | 7 - FRP Bridge Deck | CO-S1-33500 | Deck FRP Pour 5 - Waterproof segment to deck & 1B/2B CJ | 46245 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | Y | 46245 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 2 - North of River - Road Works | 7 - North of River - Road Works for Completion | CO-S1-13590 | Removal of NE Jetty - Span SL 7 Deck & beam removal, Pile Extraction | 46212 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 0-30 | Y | 46219 | Not Started | Critical | 0-10 | 0-10
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 2 - North of River - Road Works | 7 - North of River - Road Works for Completion | CO-S1-18800 | Removal of NE Jetty - Span 7 Deck & beam removal, Pile Extraction | 46206 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 0-30 | N | 46211 | Not Started | Critical | 0-10 | 0-10
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 2 - North of River - Road Works | 7 - North of River - Road Works for Completion | CO-S1-19540 | Removal of NE Jetty - Mobilisation & Fender Vibro Fender Piles 4no. | 46202 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N | CS_MSOA |  | 0-30 | 0-30 | N | 46205 | Not Started | Critical | 0-10 | 0-10
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 2 - North of River - Road Works | 7 - North of River - Road Works for Completion | CO-S1-19720 | All Temporary Jetties Removed | 46202 | CP_Phys | TT_LOE | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  |  |  | N | 46282 | Not Started | Critical | 20 and Over | 0-10
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 2 - North of River - Road Works | 7 - North of River - Road Works for Completion | CO-S1-22450 | Removal of NE Jetty - Fenders & Span 7 pile Cutting | 46220 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 0-30 | N | 46224 | Not Started | Critical | 0-10 | 0-10
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 2 - North of River - Road Works | 7 - North of River - Road Works for Completion | CO-S1-31590 | Maintenance Track & PSP - Embankment Fill | 46195 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | Y | 46206 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 2 - North of River - Road Works | 7 - North of River - Road Works for Completion | CO-S1-31600 | Maintenance Track & PSP - Drainage - Pit & Pipe - NWb-9 to NWb-7 & MT-3 to MT-1) | 46207 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | Y | 46214 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 2 - North of River - Road Works | 7 - North of River - Road Works for Completion | CO-S1-31610 | Street Lighting - Install Pits, Conduits and Foundations | 46216 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | Y | 46232 | Not Started | Not Critical | 10-20 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 2 - North of River - Road Works | 7 - North of River - Road Works for Completion | CO-S1-31620 | Maintenance Track & PSP - Subgrade Preparation | 46233 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | Y | 46235 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 2 - North of River - Road Works | 7 - North of River - Road Works for Completion | CO-S1-31630 | Maintenance Track & PSP - Sub-Base Installation | 46252 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 0-30 | Y | 46260 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 2 - North of River - Road Works | 7 - North of River - Road Works for Completion | CO-S1-31640 | Street Lighting - Install Light Poles | 46261 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 60 and above | Y | 46262 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 2 - North of River - Road Works | 7 - North of River - Road Works for Completion | CO-S1-31650 | Cut V-Drains | 46261 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 0-30 | Y | 46263 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 2 - North of River - Road Works | 7 - North of River - Road Works for Completion | CO-S1-31660 | Install Drainage Lids | 46261 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 60 and above | Y | 46263 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 2 - North of River - Road Works | 7 - North of River - Road Works for Completion | CO-S1-31670 | Final Trim, Kerb Installation & Backfill | 46265 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 60 and above | Y | 46267 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 2 - North of River - Road Works | 7 - North of River - Road Works for Completion | CO-S1-31680 | Rebuild PTA Car Park | 46265 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 60 and above | Y | 46275 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 2 - North of River - Road Works | 7 - North of River - Road Works for Completion | CO-S1-31700 | 340-360 structural backfill of external RW-M1 to underside of PTA track subbase | 46242 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 0-30 | Y | 46244 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 2 - North of River - Road Works | 7 - North of River - Road Works for Completion | CO-S1-31710 | CH340-380 PSP & PTA track Subbase, Prime and Asphalt | 46276 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 60 and above | Y | 46286 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 2 - North of River - Road Works | 7 - North of River - Road Works for Completion | CO-S1-31800 | CH 340-200 - Embankment Fill | 46298 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 0-30 | Y | 46304 | Not Started | Near Critical | 0-10 | 0-10
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 2 - North of River - Road Works | 7 - North of River - Road Works for Completion | CO-S1-31810 | CH 340-200 - Subgrade Prep & Base Course | 46305 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 0-30 | Y | 46312 | Not Started | Near Critical | 0-10 | 0-10
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 2 - North of River - Road Works | 7 - North of River - Road Works for Completion | CO-S1-31820 | Street & Arch Lighting - Install Pits, Conduits and Foundations | 46314 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 0-30 | Y | 46324 | Not Started | Near Critical | 0-10 | 0-10
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 2 - North of River - Road Works | 7 - North of River - Road Works for Completion | CO-S1-31850 | Street & Arch Lighting - Install Light Poles, terminate DB | 46325 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 0-30 | Y | 46330 | Not Started | Near Critical | 0-10 | 0-10
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 2 - North of River - Road Works | 7 - North of River - Road Works for Completion | CO-S1-31920 | Footpath Subbase, Installation and Linemarking | 46363 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 0-30 | Y | 46375 | Not Started | Critical | 10-20 | 0-10
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 2 - North of River - Road Works | 7 - North of River - Road Works for Completion | CO-S1-33610 | NW PTA stair installation | 46267 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 60 and above | Y | 46268 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 2 - North of River - Road Works | 7 - North of River - Road Works for Completion | CO-S1-33700 | Arch lighting - NW connection to bridge girder | 46245 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 0-30 | Y | 46251 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 2 - North of River - Road Works | 7 - North of River - Road Works for Completion | CO-S1-34040 | Removal of NE Jetty - Span 6 Deck & beam removal, Pile Extraction | 46225 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 0-30 | Y | 46232 | Not Started | Critical | 0-10 | 0-10
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 2 - North of River - Road Works | 7 - North of River - Road Works for Completion | CO-S1-34050 | Removal of NE Jetty - Span SL 6 Deck & beam removal, Pile Extraction | 46233 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 0-30 | Y | 46240 | Not Started | Critical | 0-10 | 0-10
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 2 - North of River - Road Works | 7 - North of River - Road Works for Completion | CO-S1-34060 | Removal of NE Jetty - Span 6 & SL 6 pile Cutting | 46241 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 0-30 | Y | 46241 | Not Started | Critical | 0-10 | 0-10
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 2 - North of River - Road Works | 7 - North of River - Road Works for Completion | CO-S1-34070 | Removal of NE Jetty - Span 5 Deck & beam removal, Pile Extraction | 46244 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 0-30 | Y | 46248 | Not Started | Critical | 0-10 | 0-10
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 2 - North of River - Road Works | 7 - North of River - Road Works for Completion | CO-S1-34080 | Removal of NE Jetty - Span 4 Deck & beam removal, Pile Extraction | 46251 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 0-30 | Y | 46255 | Not Started | Critical | 0-10 | 0-10
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 2 - North of River - Road Works | 7 - North of River - Road Works for Completion | CO-S1-34090 | Removal of NE Jetty - Span 5 & 4 pile Cutting | 46258 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 0-30 | Y | 46258 | Not Started | Critical | 0-10 | 0-10
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 2 - North of River - Road Works | 7 - North of River - Road Works for Completion | CO-S1-34100 | Removal of NE Jetty - Span 3 Deck & beam removal, Pile Extraction | 46259 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 0-30 | Y | 46265 | Not Started | Critical | 0-10 | 0-10
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 2 - North of River - Road Works | 7 - North of River - Road Works for Completion | CO-S1-34110 | Removal of NE Jetty - Span 2 Deck & beam removal, Pile Extraction | 46266 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 0-30 | Y | 46272 | Not Started | Critical | 0-10 | 0-10
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 2 - North of River - Road Works | 7 - North of River - Road Works for Completion | CO-S1-34120 | Removal of NE Jetty - Span 3 & 2 pile Cutting | 46273 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 0-30 | Y | 46273 | Not Started | Critical | 0-10 | 0-10
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 2 - North of River - Road Works | 7 - North of River - Road Works for Completion | CO-S1-34130 | Removal of NE Jetty - Span 1 Deck & beam removal, Pile Extraction | 46274 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 0-30 | Y | 46279 | Not Started | Critical | 0-10 | 0-10
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 2 - North of River - Road Works | 7 - North of River - Road Works for Completion | CO-S1-34140 | Removal of NE Jetty - Span 1 pile Cutting | 46280 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 0-30 | Y | 46280 | Not Started | Critical | 0-10 | 0-10
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 2 - North of River - Road Works | 7 - North of River - Road Works for Completion | CO-S1-34390 | Removal of NE Jetty - Pack up & Demob | 46282 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 0-30 | Y | 46282 | Not Started | Critical | 0-10 | 0-10
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 2 - North of River - Road Works | 7 - North of River - Road Works for Completion | CO-S1-34680 | Reconfigure NE crane | 46185 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 0-30 | Y | 46191 | Not Started | Critical | 0-10 | 0-10
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 2 - North of River - Road Works | 7 - North of River - Road Works for Completion | CO-S1-34850 | Maintenance Track & PSP - Drainage - Pit & Pipe - Outlet to NWb-9 | 46183 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | Y | 46193 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 3 - South of River - Road Works | 7 - South of River - Road Works for Completion | CO-S1-23230 | PSP - Road Markings & Signage | 46287 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 60 and above | N | 46288 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 3 - South of River - Road Works | 7 - South of River - Road Works for Completion | CO-S1-23240 | PSP - Subgrade Prep | 46251 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | N | 46252 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 3 - South of River - Road Works | 7 - South of River - Road Works for Completion | CO-S1-23250 | PSP - Security Fencing | 46287 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 60 and above | N | 46288 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 3 - South of River - Road Works | 7 - South of River - Road Works for Completion | CO-S1-23260 | PSP - Surfacing | 46276 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | N | 46286 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 3 - South of River - Road Works | 7 - South of River - Road Works for Completion | CO-S1-23270 | PSP - Excavate / Fill to Subgrade Level | 46224 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 60 and above | N | 46227 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 3 - South of River - Road Works | 7 - South of River - Road Works for Completion | CO-S1-23280 | PSP - Subbase | 46253 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | N | 46258 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 3 - South of River - Road Works | 7 - South of River - Road Works for Completion | CO-S1-23300 | PSP - Exc, Lay & B/fill Drains | 46228 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 60 and above | N | 46230 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 3 - South of River - Road Works | 7 - South of River - Road Works for Completion | CO-S1-23320 | PSP - Lighting Pits, Conduits, footings and plinth for CoF SWB | 46244 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | N | 46249 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 3 - South of River - Road Works | 7 - South of River - Road Works for Completion | CO-S1-23630 | Removal of SE Jetty - Summary | 46213 | CP_Phys | TT_LOE | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  |  |  | N | 46242 | Not Started | Not Critical | 20 and Over | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 3 - South of River - Road Works | 7 - South of River - Road Works for Completion | CO-S1-24460 | REDACTED St Reconstruction | 46294 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | N | 46312 | Not Started | Not Critical | 10-20 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 3 - South of River - Road Works | 7 - South of River - Road Works for Completion | CO-S1-31460 | REDACTED St Drainage | 46267 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | Y | 46283 | Not Started | Not Critical | 10-20 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 3 - South of River - Road Works | 7 - South of River - Road Works for Completion | CO-S1-31470 | Post-SW Jetty Removal Reinstatement Works | 46197 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 60 and above | Y | 46206 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 3 - South of River - Road Works | 7 - South of River - Road Works for Completion | CO-S1-31480 | Gate 3 Reinstatement & Kerbing | 46207 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 60 and above | Y | 46227 | Not Started | Not Critical | 10-20 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 3 - South of River - Road Works | 7 - South of River - Road Works for Completion | CO-S1-31490 | Post-SE Jetty Removal Reinstatement Works | 46244 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | Y | 46255 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 3 - South of River - Road Works | 7 - South of River - Road Works for Completion | CO-S1-31980 | Revetment Installation Under and East of Bridge | 46256 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | Y | 46284 | Not Started | Not Critical | 20 and Over | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 3 - South of River - Road Works | 7 - South of River - Road Works for Completion | CO-S1-33720 | PSP - Lighting - Install CoF SWB & light poles | 46286 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | Y | 46296 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 3 - South of River - Road Works | 7 - South of River - Road Works for Completion | CO-S1-33730 | MRWA light poles installed and terminated | 46228 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 60 and above | Y | 46233 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 3 - South of River - Road Works | 7 - South of River - Road Works for Completion | CO-S1-34170 | Removal of SW Jetty - Span SL 2 Deck & beam removal, Pile Extraction | 46164 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_Active | N |  |  | 0-30 | 30-60 | Y | 46170 | In Progress | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 3 - South of River - Road Works | 7 - South of River - Road Works for Completion | CO-S1-34180 | Removal of SW Jetty - Fender & Span 3 & SL 2 pile Cutting | 46171 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | Y | 46176 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 3 - South of River - Road Works | 7 - South of River - Road Works for Completion | CO-S1-34190 | Removal of SW Jetty - Span 2 Deck & beam removal, Pile Extraction | 46177 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | Y | 46184 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 3 - South of River - Road Works | 7 - South of River - Road Works for Completion | CO-S1-34200 | Removal of SW Jetty - Span 1 Deck & beam removal, Pile Extraction | 46185 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | Y | 46192 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 3 - South of River - Road Works | 7 - South of River - Road Works for Completion | CO-S1-34210 | Removal of SW Jetty - Span 2 & 1 pile Cutting | 46195 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | Y | 46195 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 3 - South of River - Road Works | 7 - South of River - Road Works for Completion | CO-S1-34220 | Removal of SE Jetty - Mobilisation | 46213 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | Y | 46213 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 3 - South of River - Road Works | 7 - South of River - Road Works for Completion | CO-S1-34230 | Removal of SE Jetty - Span 2 Deck & beam removal, Pile Extraction | 46214 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | Y | 46221 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 3 - South of River - Road Works | 7 - South of River - Road Works for Completion | CO-S1-34240 | Removal of SE Jetty - Span SL 2 Deck & beam removal, Pile Extraction | 46223 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | Y | 46231 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 3 - South of River - Road Works | 7 - South of River - Road Works for Completion | CO-S1-34250 | Removal of SE Jetty - Span 2 & SL 2 pile Cutting | 46232 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | Y | 46232 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 3 - South of River - Road Works | 7 - South of River - Road Works for Completion | CO-S1-34260 | Removal of SE Jetty - Span 1 Deck & beam removal, Pile Extraction | 46233 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | Y | 46238 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 3 - South of River - Road Works | 7 - South of River - Road Works for Completion | CO-S1-34270 | Removal of SE Jetty - Span 1 pile Cutting | 46239 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | Y | 46239 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 3 - South of River - Road Works | 7 - South of River - Road Works for Completion | CO-S1-34370 | Removal of SE Jetty - Pack up & Demob | 46240 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | Y | 46242 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 3 - South of River - Road Works | 7 - South of River - Road Works for Completion | CO-S1-34380 | Removal of SW Jetty - Pack up & Demob | 46196 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 30-60 | Y | 46196 | Not Started | Not Critical | 0-10 | 20 and Over
2 - DELIVERY PHASE | 8 - Construction | 4 - SP1 - Main Works Scope | 2 - Road Works | 3 - South of River - Road Works | 7 - South of River - Road Works for Completion | CO-S1-35310 | PSP - Install 4 rail barrier - construct pad, last 6 pile and install rails | 46202 | CP_Phys | TT_Task | DT_FixedDUR2 | RV_OK | TK_NotStart | N |  |  | 0-30 | 60 and above | Y | 46232 | Not Started | Not Critical | 10-20 | 20 and Over